## Basic Agile Project with Gantt
At Risk | Task Name | Feature Type | Story Points | Duration | Start | Finish | Predecessors | Status | Sprint | Team | Notes
| FIMpy - File Integrity Monitoring |  |  | 47d | 2017-10-09 | 2017-12-12
| Sprints |  |  | 47d | 2017-10-09 | 2017-12-12
| Sprint 1 |  | 33 | 17.5d | 2017-10-09 | 2017-11-01
| Python Flask Headless App | Core | 8 | 11d | 2017-10-09 | 2017-10-23 |  | Complete | 1
| Prototype app with simple REST "ping" service |  |  | 2d | 2017-10-09 | 2017-10-10
| File scanning functionality |  |  | 4d | 2017-10-11 | 2017-10-16
| Vacation |  |  | 6d | 2017-10-16 | 2017-10-23
TRUE | HMAC and Hash Calculation | Security | 5 | 4d | 2017-10-23 | 2017-10-26 |  | Complete | 1
| Hashing function for scanned file |  |  | 4d | 2017-10-23 | 2017-10-26
HMAC calculation using hard-coded key
| REST micro-services Integrity functionality | Account Management | 20 | 7.5d | 2017-10-23 | 2017-11-01 |  | Complete
| REST micro-service to invoke HMAC calculation |  |  | 1.5d | 2017-10-23 | 2017-10-24 |  | Complete
| REST micro-service to verify HMAC |  |  | 2d | 2017-10-26 | 2017-10-27 |  | Complete
| REST micro-service to invoke HMAC calculation |  |  | 2.5d | 2017-10-30 | 2017-11-01 |  | Complete
| Sprint 2 |  | 21 | 15.5d | 2017-11-01 | 2017-11-22 | 3
| Database Support |  | 13 | 15.5d | 2017-11-01 | 2017-11-22 |  | Complete | 2
| Alerting using slack | Maintenance | 5 | 1d | 2017-11-01 | 2017-11-02 |  | Complete | 2
| Authentication & Authorisation using LDAP |  | 3 | 1d | 2017-11-01 | 2017-11-02 |  | Complete | 2
| Sprint 3 |  | 21 | 14d | 2017-11-23 | 2017-12-12 | 15
TRUE | Implement KeyProtect Secure Keys for HMAC |  | 3 | 1d | 2017-11-23 | 2017-11-23 |  | Complete | 3
| FIMpy Status Dashboard |  | 5 | 1d | 2017-11-23 | 2017-11-23 |  | Complete | 3
| Alerting using slack |  | 3 | 8d | 2017-11-23 | 2017-12-04 |  | Complete | 3
| Project Report |  | 10 | 14d | 2017-11-23 | 2017-12-12 |  | In Progress
| Backlog |  | 0
| CA certs | [6 empty] | Not Started | Backlog